## To Be (edits marked)
Midmarket Support Center (MSC) RACI Matrix - To-Be Process (Project Mgmt & Estimating in MSC)
|  | Branch | [8 empty] | MSC
| PROCESS TASKS | Sales | Sales Mgr1 | Ops Mgr | BGM | PM Tasks2 | Project Coordinator | Tech/Eng Spec | Procurement | Central Book/Bill | Ops Manager | PM Tasks2 | Design Engineer | Tech PM (delete) | Drafter | Procurement3 | Branch/Zone CoC Tasks | MSC Tasks | Comments:
Acquisition | Customer or contractor request for pricing. | RA | [16 empty] | RACI: R - Responsible, A - Accepts (Approves), C - Contributes, I - Informed Note 1: In smaller branches, Sales Mgr is the BGM Note 2: MSC PM Tasks = Associate Project Manager or Engineering Specialist
PM010 - Ensure Management approval of the project (Go/No)
| Project Request Logged and Forecasted (Email Notification Sent to Sales/Ops. Manager) | RA | I
| Enter Prospect Information In CRM Tool and Create Opportunity | RA
| Identify Stakeholders (Contact Information Documented by) Operations ability to Execute | R | A | [7 empty] | C
| Create and agree with the customer on project structure | R | A
| Design Price Consideration (If yes get booking approval) | R | A | [7 empty] | I
PM020 - Management approval of the project (Bid no Bid)
Bid Preparation | Review Project Plans | R | [10 empty] | C | [5 empty] | During startup, use Branch Estimator in Austin, directed by MSC. As we expand, MSC will hire dedicated Estimator. Note 3: MSC Procurement in this case would be a corporate resources (e.g., Nate Richardson). Number of subcontractor bids based on $ amount of sub content: >$50k content = 5 bids >$25k, <$50k = 3 bids <$25k = 1 bid
| Review Project Specifications (note meeting expectations, inc. safety and project reviews) | R
| Review Contract and or General terms and Conditions | R
| Review and Document the Scope of the Project | R | [10 empty] | C
| Walk the site to verify site conditions | R
| Determine Budget | R
| Create Final Project Scope Document | R | [10 empty] | C
| Define and Estimate Cost Elements (Material) | I | [10 empty] | R |  |  | C
| Define and Estimate Activities (Branch field labor and MSC engineering labor) | C |  | I |  | C | [5 empty] | R | C
| Review Activity Sequence and Schedule | I |  | I |  | R | [5 empty] | R | C
| Identify Risk (any identified risk added to estimate - no RAT needed) | R | A |  |  | C | [5 empty] | C | C
| Complete the cost review checklist (Dan & Damian to review) | R |  |  |  | C | [5 empty] | C | C
| Get required Subcontractor Bid (Electrical RFP) based on content value. | I |  |  |  | C | [5 empty] | C |  |  |  | R
| Create Bid Estimate | R
| Pre-Bid Review of all required Documents | R |  | C |  |  |  |  | I |  |  |  | C
| Price and margin set | R | A
PM040 - Bid Approval (Cost Review in Opportunity in Turbo Sales)
Contract Negotiation | Send Proposal Scope and Estimate | R | [16 empty] | If branch has sales coordinator, this may transition to them (confirm with BGMs)
| Contract Negotiation of terms and conditions | R
| Follow-up on Status and Timing of the Order | R
| Receive Contract or PO from Customer/Mechanical Contractor to start | R
| Create booking package for approval and Booking in SAP (Frozen Sales Estimate) | R | A
| Select Project Manager | I |  | I |  | I |  |  |  |  | R | I
| Document and store all project information in preparation for booking and execution | R |  |  |  |  | I |  |  |  |  | I | I
| After approvals are received, complete quality check | [8 empty] | R
| Book project, update SAP and update TurboSales to indicate booking | I | I |  |  | I | I |  |  | R |  | I | I
PM070 - Book the project in SAP
Project Hand-over | Sales to Operations Turnover (Within 5 days of confirmation of order) | R |  |  |  | C | C |  |  |  |  | C | C
| Review Customer Requirements/Plans & Specs/Contracts and Document Project Scope |  |  |  |  | R | [5 empty] | R | C
| Review the Estimate Cost Items, Schedule, and Risk Items Idenfified during Pre-Bid |  |  |  |  | R | [5 empty] | R | C
PM080 - Set PM@SIEMENS (PM080) Within 2 days of meeting.
Project Opening and Clarification | "Make Contact Step One" Introduction with Contractor / Customer, introduce remote PM | R |  |  |  | I | [5 empty] | I | [6 empty] | MSC Involved for panels and/or VAV installed at Mfgr
| Update Project Contact List (Communication Plan) | C |  |  |  | R | [5 empty] | R
| Assess Needs and Urgent customer Concerns, Order Early Material as needed | C |  |  |  | R | [5 empty] | R | C |  |  | C
| Create Project Schedule for Customer Approval | I |  |  |  | R | [5 empty] | R | C
| Finalize Project Plan | I |  |  |  | R | [5 empty] | R
PM100 - Operations Reviews & Accepts Budget (within 30 days)
Detailed Planning | PM to Organize Project Documents Required for Design |  |  |  |  | R | [5 empty] | R | [6 empty] | Request for information RFI - engineering will be initiated from MSC, schedule queries will come from Branch PM
| Assign Design Task (Execute Design Process) |  |  |  |  | R | [5 empty] | R | C
| Create Billing Schedule of values (AIA Document) Plan for 3 to 5 billings |  |  |  |  | R | [5 empty] | R
| Request For Approved Equipment Data (Sales may need to present MC/Customer locally) | C |  |  |  | R | [5 empty] | R | C
| Request for other needed information "RFI" | I |  |  |  | R | [5 empty] | R | C
| Review Activity Sequence and Schedule |  |  |  |  | R | [5 empty] | R | C
| Complete Design Package |  |  |  |  | R | [5 empty] | R | C |  | C
| Define and Re-estimate Cost Elements (All cost elements) |  |  |  |  | R | [5 empty] | R
| Ensure Procurement Cost Saving Considerations are being Utilized | [11 empty] | R
| Submit Change orders and revise Committed Cost as Needed | I |  |  |  | R | [5 empty] | R | C
| Quality Review of Design Package |  |  |  |  | R | [5 empty] | R | C
| PM Approves Design Package Prior to Submittal being sent to Customer/Engineer |  |  |  |  | R | [5 empty] | R
| Update project template in Wrike |  |  |  |  | R | [5 empty] | R | C
| Maintain JTD POC % for Billing CIE JTD |  |  |  |  | R | [5 empty] | R
Detailed Design Complete
Purchasing and Dispatch | Turnover hard copy (via BlueBeam) blue prints for installer (subcontractor or in-house electrical) |  |  |  |  | R | [5 empty] | R | C | [5 empty] | BG Procurement may be involved for sheet metal buying, e.g.
| Procurement of Subcontractors (upon approval) Contract executed with vendor |  |  |  |  | R | C |  | I |  |  | R
Purchase Siemens and Third Party Materials (coordinate lead times w/PM)
| Track Shipments to ensure Deliveries |  |  |  |  | R | [5 empty] | R |  |  |  | C
| Coordinate factory mounted controls (these decisions are made during design phase) |  |  |  |  | I | [5 empty] | I | R |  |  | C
| Maintain JTD POC % for Billing CIE JTD |  |  |  |  | R |  |  |  | C |  | R
| Review of Installation Requirements with Sub |  |  |  |  | R | [5 empty] | R
| Monthly Material Expediting Inventory and Tracking |  |  |  |  | R | [5 empty] | R | C |  |  | C
Procurement of Material (upon approval)
Technical Execution Commission Install | Perform Monthly Billing |  |  |  |  | R |  |  |  | C |  | R | [6 empty] | "Direct and Manage Project Execution" includes MSC Design Engineer support for pack and go for DXR's (blaster files for TEC)
| Acquire and Coordinate Field Resources (Branch and other resources) |  |  | C |  | R | [5 empty] | R
| Direct and Manage Project Execution |  |  |  |  | R | [5 empty] | R | C
Perform/monitor Site installation (Assurance of Quality)
| Monthly Labor Planning and Scheduling |  |  |  |  | R | [5 empty] | R | [6 empty] | Can MSC use tools to help automate commissioning? TBC for DXR? Smart Building Recorder to remotely commission BACnet DXR's expected in June 2018.
| Monthly Revenue Forecasting (will need to factor this into Project Controlling Process setup) |  |  |  |  | R | [5 empty] | R
| Monitor Risk (Update Risk Registery in PMCT if necessary) |  |  |  |  | R | [5 empty] | R
| Monthly Change order Management | C |  |  |  | R | [5 empty] | R
| Verify Scope completeness (Quality Control) | C |  |  |  | R | [5 empty] | R | C
| Continually document changes "redline prep for As-builts" |  |  |  |  | R | [5 empty] | R | C
| Asbuilt AutoCAD work assigned |  |  |  |  | R | [5 empty] | R | C |  | C
| Archive of project specific documentation |  |  |  |  | R | C |  |  |  |  | R
| Resolve Punch list Items | C |  |  |  | R | [5 empty] | R
| Customer Training Preparation/Scheduling | R |  |  |  | C | [5 empty] | C
| Commissioning (remote commissioning will need to be conducted by org comparable to RCS TOC) |  |  |  |  | R | [5 empty] | R | C
| Submit Commissioning Documentation MSC Design Engineer | C |  |  |  | R | [5 empty] | R | C
| PM to inform Customer that installation is ready for Site Acceptance Test | C |  |  |  | R | [5 empty] | R
Release for Customer Acceptance
Acceptance | Resolve Punch list Items | C |  |  |  | R | [5 empty] | R
| Verify Terms of the Contract are Complete |  |  |  |  | R | [5 empty] | R
| Perform Customer Training | R |  |  |  | C | [5 empty] | C
| Submit Final Customer Documentation |  |  |  |  | R | [5 empty] | R
| Customer Acceptance (PM 650) Create/send warranty letter | I |  |  |  | I | R |  |  |  |  | I
Warranty Documentation complete
Close | Ensure final cost and Final Billing |  |  |  |  | R | C |  |  | C |  | R
| Verify All Actual and Committed cost are posted to the Project (Close Procurement) |  |  |  |  | R | C |  |  |  |  | R
| Document Lessons Learned (if required - if GM slips by 10% or more) | C | I |  |  | R | [5 empty] | R | C
PM670 - Close Project in SAP (Close Project or Phase)
Warranty | Solutions to Service Turnover | I |  | C | C | R | C |  |  |  |  | R
PM700 - End of Warranty

## Interim Process
Midmarket Support Center (MSC) RACI Matrix - Interim Process (Project Mgmt in branch)
|  | Branch | [8 empty] | MSC | [6 empty] | Document Number
| PROCESS TASKS | Sales | Sales Mgr1 | Ops Mgr | BGM | PM Tasks2 | Project Coordinator | Tech/Eng Spec | Procurement | Central Book/Bill | Ops Manager | Design Engineer | Tech PM (delete) | Drafter | Procurement3 | Branch/Zone CoC Tasks | MSC Tasks |  | Comments:
Acquisition | Customer or contractor request for pricing. | RA | [15 empty] | 1.1 | RACI: R - Responsible, A - Accepts (Approves), C - Contributes, I - Informed Note 1: In smaller branches, Sales Mgr is the BGM Note 2: Branch PM Tasks = Associate Project Manager or Engineering Specialist
PM010 - Ensure Management approval of the project (Go/No)
| Project Request Logged and Forecasted (Email Notification Sent to Sales/Ops. Manager) | RA | I | [14 empty] | 1.2
| Enter Prospect Information In CRM Tool and Create Opportunity | RA | [15 empty] | 1.3
| Identify Stakeholders (Contact Information Documented by) Operations ability to Execute | R | A | [7 empty] | C | [6 empty] | 1.4
| Create and agree with the customer on project structure | R | A | [14 empty] | 1.5
| Design Price Consideration (If yes get booking approval) | R | A | [7 empty] | I | [6 empty] | 1.6
PM020 - Management approval of the project (Bid no Bid)
Bid Preparation | Review Project Plans | R | [9 empty] | C | [5 empty] | 2.1 | During startup, use Branch Estimator in Austin, directed by MSC. As we expand, MSC will hire dedicated Estimator. Note 3: MSC Procurement in this case would be a corporate resources (e.g., Nate Richardson). Number of subcontractor bids based on $ amount of sub content: >$50k content = 5 bids >$25k, <$50k = 3 bids <$25k = 1 bid
| Review Project Specifications (note meeting expectations, inc. safety and project reviews) | R | [15 empty] | 2.2
| Review Contract and or General terms and Conditions | R | [15 empty] | 2.3
| Review and Document the Scope of the Project | R | [9 empty] | C | [5 empty] | 2.4
| Walk the site to verify site conditions | R | [15 empty] | 2.5
| Determine Budget | R | [15 empty] | 2.6
| Create Final Project Scope Document | R | [9 empty] | C | [5 empty] | 2.7
| Define and Estimate Cost Elements (Material) | I | [9 empty] | R |  |  | C |  |  | 2.8
| Define and Estimate Activities (Branch field labor and MSC engineering labor) | R |  | I |  | C | [5 empty] | C | [5 empty] | 2.9
| Review Activity Sequence and Schedule | I |  | I |  | R | [5 empty] | C | [5 empty] | 2.10
| Identify Risk (any identified risk added to estimate - no RAT needed) | R | A |  |  | C | [5 empty] | C | [5 empty] | 2.11
| Complete the cost review checklist (Dan & Damian to review) | R |  |  |  | C | [5 empty] | C | [5 empty] | 2.12
| Get required Subcontractor Bid (Electrical RFP) based on content value. | I |  |  |  | C | [8 empty] | R |  |  | 2.13
| Create Bid Estimate | R | [15 empty] | 2.14
| Pre-Bid Review of all required Documents | R |  | C |  |  |  |  | I |  |  | C | [5 empty] | 2.15
| Price and margin set | R | A | [14 empty] | 2.16
PM040 - Bid Approval (Cost Review in Opportunity in Turbo Sales)
Contract Negotiation | Send Proposal Scope and Estimate | R | [15 empty] | 3.1 | If branch has sales coordinator, this may transition to them (confirm with BGMs)
| Contract Negotiation of terms and conditions | R | [15 empty] | 3.2
| Follow-up on Status and Timing of the Order | R | [15 empty] | 3.3
| Receive Contract or PO from Customer/Mechanical Contractor to start | R | [15 empty] | 3.4
| Create booking package for approval and Booking in SAP (Frozen Sales Estimate) | R | A | [14 empty] | 3.5
| Select Project Manager | I |  | R |  | I |  |  |  |  | I | [6 empty] | 3.6
| Document and store all project information in preparation for booking and execution | R |  |  |  |  | I |  |  |  |  | I | [5 empty] | 3.7
| After approvals are received, complete quality check | [8 empty] | R | [7 empty] | 3.8
| Book project, update SAP and update TurboSales to indicate booking | I | I |  |  | I | I |  |  | R |  | I | [5 empty] | 3.9
PM070 - Book the project in SAP
Project Hand-over | Sales to Operations Turnover (Within 5 days of confirmation of order) | R |  |  |  | C | C |  |  |  |  | C | [5 empty] | 4.1
| Review Customer Requirements/Plans & Specs/Contracts and Document Project Scope |  |  |  |  | R | [5 empty] | C | [5 empty] | 4.2
| Review the Estimate Cost Items, Schedule, and Risk Items Idenfified during Pre-Bid |  |  |  |  | R | [5 empty] | C | [5 empty] | 4.3
PM080 - Set PM@SIEMENS (PM080) Within 2 days of meeting.
Project Opening and Clarification | "Make Contact Step One" Introduction with Contractor / Customer, introduce remote PM | R |  |  |  | I | [11 empty] | 5.1 | MSC Involved for panels and/or VAV installed at Mfgr
| Update Project Contact List (Communication Plan) | C |  |  |  | R | [11 empty] | 5.2
| Assess Needs and Urgent customer Concerns, Order Early Material as needed | C |  |  |  | R | [5 empty] | C |  |  | C |  |  | 5.3
| Create Project Schedule for Customer Approval | I |  |  |  | R | [5 empty] | C | [5 empty] | 5.4
| Finalize Project Plan | I |  |  |  | R | [11 empty] | 5.5
PM100 - Operations Reviews & Accepts Budget (within 30 days)
Detailed Planning | PM to Organize Project Documents Required for Design |  |  |  |  | R | [11 empty] | 6.1 | Request for information RFI - engineering will be initiated from MSC, schedule queries will come from Branch PM
| Assign Design Task (Execute Design Process) |  |  |  |  | R | [5 empty] | C | [5 empty] | 6.2
| Create Billing Schedule of values (AIA Document) Plan for 3 to 5 billings |  |  |  |  | R | [11 empty] | 6.3
| Request For Approved Equipment Data (Sales may need to present MC/Customer locally) | C |  |  |  | R | [5 empty] | C | [5 empty] | 6.4
| Request for other needed information "RFI" | I |  |  |  | R | [5 empty] | C | [5 empty] | 6.5
| Review Activity Sequence and Schedule |  |  |  |  | R | [5 empty] | C | [5 empty] | 6.6
| Complete Design Package |  |  |  |  | R | [5 empty] | C |  | C |  |  |  | 6.7
| Define and Re-estimate Cost Elements (All cost elements) |  |  |  |  | R | [11 empty] | 6.8
| Ensure Procurement Cost Saving Considerations are being Utilized | [10 empty] | R | [5 empty] | 6.9
| Submit Change orders and revise Committed Cost as Needed | I |  |  |  | R | [5 empty] | C | [5 empty] | 6.10
| Quality Review of Design Package |  |  |  |  | R | [5 empty] | C | [5 empty] | 6.11
| PM Approves Design Package Prior to Submittal being sent to Customer/Engineer |  |  |  |  | R | [11 empty] | 6.12
| Update project template in Wrike |  |  |  |  | R | [5 empty] | C | [5 empty] | 6.13
| Maintain JTD POC % for Billing CIE JTD |  |  |  |  | R | [11 empty] | 6.14
Detailed Design Complete
Purchasing and Dispatch | Turnover hard copy (via BlueBeam) blue prints for installer (subcontractor or in-house electrical) |  |  |  |  | R | [5 empty] | C | [5 empty] | 7.1 | BG Procurement may be involved for sheet metal buying, e.g.
| Procurement of Subcontractors (upon approval) Contract executed with vendor |  |  |  |  | R | C |  | I | [8 empty] | 7.2
Purchase Siemens and Third Party Materials (coordinate lead times w/PM)
| Track Shipments to ensure Deliveries |  |  |  |  | R | [8 empty] | C |  |  | 8.1
| Coordinate factory mounted controls (these decisions are made during design phase) |  |  |  |  | I | [5 empty] | R |  |  | C |  |  | 8.2
| Maintain JTD POC % for Billing CIE JTD |  |  |  |  | R |  |  |  | C | [7 empty] | 8.3
| Review of Installation Requirements with Sub |  |  |  |  | R | [11 empty] | 8.4
| Monthly Material Expediting Inventory and Tracking |  |  |  |  | R | [5 empty] | C |  |  | C |  |  | 8.5
Procurement of Material (upon approval)
Technical Execution Commission Install | Perform Monthly Billing |  |  |  |  | R |  |  |  | C | [7 empty] | 9.1 | "Direct and Manage Project Execution" includes MSC Design Engineer support for pack and go for DXR's (blaster files for TEC)
| Acquire and Coordinate Field Resources (Branch and other resources) |  |  | C |  | R | [11 empty] | 9.2
| Direct and Manage Project Execution |  |  |  |  | R | [5 empty] | C | [5 empty] | 9.3
Perform/monitor Site installation (Assurance of Quality)
| Monthly Labor Planning and Scheduling |  |  |  |  | R | [11 empty] | 9.4 | Can MSC use tools to help automate commissioning? TBC for DXR? Smart Building Recorder to remotely commission BACnet DXR's expected in June 2018.
| Monthly Revenue Forecasting (will need to factor this into Btworks setup) |  |  |  |  | R | [11 empty] | 9.5
| Monitor Risk (Update Risk Registery in PMCT if necessary) |  |  |  |  | R | [11 empty] | 9.6
| Monthly Change order Management | C |  |  |  | R | [11 empty] | 9.7
| Verify Scope completeness (Quality Control) | C |  |  |  | R | [5 empty] | C | [5 empty] | 9.8
| Continually document changes "redline prep for As-builts" |  |  |  |  | R | [5 empty] | C | [5 empty] | 9.9
| Asbuilt AutoCAD work assigned |  |  |  |  | R | [5 empty] | C |  | C |  |  |  | 9.10
| Archive of project specific documentation |  |  |  |  | R | C | [10 empty] | 9.11
| Resolve Punch list Items | C |  |  |  | R | [11 empty] | 9.12
| Customer Training Preparation/Scheduling | R |  |  |  | C | [11 empty] | 9.13
| Commissioning (remote commissioning will need to be conducted by org comparable to RCS TOC) |  |  |  |  | R | [5 empty] | C | [5 empty] | 9.14
| Submit Commissioning Documentation MSC Design Engineer | C |  |  |  | R | [5 empty] | C | [5 empty] | 9.15
| PM to inform Customer that installation is ready for Site Acceptance Test | C |  |  |  | R | [11 empty] | 9.16
Release for Customer Acceptance
Acceptance | Resolve Punch list Items | C |  |  |  | R | [11 empty] | 10.1
| Verify Terms of the Contract are Complete |  |  |  |  | R | [11 empty] | 10.2
| Perform Customer Training | R |  |  |  | C | [11 empty] | 10.3
| Submit Final Customer Documentation |  |  |  |  | R | [11 empty] | 10.4
| Customer Acceptance (PM 650) Create/send warranty letter | I |  |  |  | I | R | [10 empty] | 10.5
Warranty Documentation complete
Close | Ensure final cost and Final Billing |  |  |  |  | R | C |  |  | C | [7 empty] | 11.1
| Verify All Actual and Committed cost are posted to the Project (Close Procurement) |  |  |  |  | R | C | [10 empty] | 11.2
| Document Lessons Learned (if required - if GM slips by 10% or more) | C | I |  |  | R | [5 empty] | C | [5 empty] | 11.3
PM670 - Close Project in SAP (Close Project or Phase)
Warranty | Solutions to Service Turnover | I |  | C | C | R | C
PM700 - End of Warranty